# IRB Data Request Log

Project Status: Active, in progress

Unit: Research and Compliance

Report refreshed: 2026-07-29

# Overview

A single log of every data request that comes through the institutional review board, with what was asked for, what was released, and under which approval. Replaces an email thread and a shared inbox.

# Project Driving Questions

Question

What is the current turnaround time from request to data release?

Which requests are waiting on us and which are waiting on the requester?

What data elements get requested most often, and should they be a standing extract?

# Team

| Name | Role |
| --- | --- |
| Elaine Cordova | Project lead |
| Nathan Iwu | Compliance analyst |
| Bethany Kroll | IRB coordinator |

# Milestones

| Milestone | Target | Status |
| --- | --- | --- |
| Historical requests backfilled from email | 2026-05-30 | Done |
| Intake form live | 2026-06-27 | Done |
| Turnaround reporting in place | 2026-08-07 | In progress |
| Standing extract catalog published | 2026-09-11 | Not started |

# Tasks

| Task | Status |
| --- | --- |
| Backfill the last two years of requests | Done |
| Design and publish the intake form | Done |
| Define the turnaround clock and when it pauses | Done |
| Build the turnaround report | In progress |
| Identify the most requested elements | In progress |
| Draft the standing extract catalog | Not started |

# Log

| Date | Update |
| --- | --- |
| 2026-06-11 | Backfill finished, 214 historical requests logged. |
| 2026-06-27 | Intake form went live, first four requests came through it the same week. |
| 2026-07-15 | Agreed the turnaround clock pauses while a request sits with the requester. |
| 2026-07-23 | Turnaround report skeleton built, median sits at 11 working days. |
| 2026-07-28 | Element frequency counts drafted, enrollment and demographics dominate. |

# Decisions

| Date | Decision | Rationale |
| --- | --- | --- |
| 2026-07-15 | Turnaround clock pauses when the request is with the requester | Measures what we control rather than total elapsed time |

# Links

| Resource | Location |
| --- | --- |
| Request log | Research Compliance / IRB / request-log |
| Intake form | Research Compliance / IRB / intake |
| Turnaround report | Division Analytics / Research / irb-turnaround |

# Notes

The pause rule matters a lot. Raw elapsed time made us look far slower than we are, because most long requests are long while sitting with the requester.

Roughly a third of requests ask for the same handful of elements. Those are the candidates for a standing extract.