# Research Expenditures Reporting

Project Status: In review with the research office

Unit: Research and Compliance

Report refreshed: 2026-07-29

# Overview

Annual research expenditure reporting, assembled from the finance system and reconciled against sponsored programs records before it goes to federal survey submission. Accuracy matters more than speed here.

# Project Driving Questions

Question

What did the institution spend on research this year, by field and by funding source?

Where do finance and sponsored programs disagree, and why?

How does the expenditure trend compare to peer institutions?

Which fund groups moved between years, and does the prior year need restating?

What share of expenditure passes through to subaward recipients?

# Team

| Name | Role |
| --- | --- |
| Gordon Pike | Project lead |
| Aisha Nabulsi | Finance analyst |
| Victor Sandoval | Sponsored programs liaison |
| Priya Raghunathan | Institutional research analyst |
| Harriet Nkemelu | Controller office contact |

# Milestones

| Milestone | Target | Status |
| --- | --- | --- |
| Annual cycle opened with the research office | 2026-06-17 | Done |
| Finance extract reconciled | 2026-06-25 | Done |
| Field of science mapping refreshed | 2026-06-30 | Done |
| Peer comparison set agreed | 2026-07-13 | Done |
| Draft submission assembled | 2026-07-22 | Done |
| Research office sign off | 2026-08-12 | In progress |

# Tasks

| Task | Status |
| --- | --- |
| Pull the finance expenditure extract | Done |
| Reconcile against sponsored programs totals | Done |
| Refresh the field of science crosswalk | Done |
| Agree the peer comparison set | Done |
| Resolve the clinical trials fund group treatment | Done |
| Assemble the draft submission | Done |
| Walk the research office through the variances | In progress |
| Write the subaward timing footnote | In progress |
| Prepare the peer comparison pack for leadership | Not started |
| Submit the final figures | Not started |

# Release Schedule

| Release | Env | Target | Shipped | Status |
| --- | --- | --- | --- | --- |
| FY26.1 | Internal | 2026-06-25 | 2026-06-25 | Shipped |
| FY26.2 | Research office | 2026-07-22 | 2026-07-22 | Shipped |
| FY26.3 | Research office | 2026-08-12 |  | Open |
| FY26.4 | Federal | 2026-10-01 |  | Planned |

# Feature Requests

| Item | Request | From | Received | Target Drop | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Break expenditures out by college as well as field of science | Renata Alvarez | 2026-06-24 | FY26.2 | Done |
| 2 | Report clinical trials income separately from other sponsored activity | Harriet Nkemelu | 2026-07-02 | FY26.2 | Done |
| 3 | Show subaward pass through as its own line | Victor Sandoval | 2026-07-15 | FY26.3 | Open |
| 4 | Three year trend by funding source for the board packet | Harriet Nkemelu | 2026-07-24 | FY26.3 | Open |
| 5 | Peer comparison slide for the leadership pack | Cynthia Vale | 2026-07-27 | FY26.3 | Done |
| 6 | Restate the last five years on the new fund grouping | Renata Alvarez | 2026-07-28 | FY26.4 | Open |
| 7 | Monthly expenditure tracking through the year | Various | 2026-07-06 |  | Declined |

# Log

| Date | Update |
| --- | --- |
| 2026-06-17 | Annual cycle opened with the research office, submission window confirmed as 2026-10-01. |
| 2026-06-19 | Finance expenditure extract pulled for the year, 4,180 award lines. |
| 2026-06-22 | First pass reconciliation against sponsored programs, 2.1 percent gap sitting in subawards. |
| 2026-06-25 | Gap narrowed to 0.4 percent once cost share bookings were excluded. |
| 2026-06-29 | Field of science crosswalk refreshed, twelve new subaward mappings added. |
| 2026-07-01 | Started the peer comparison pull from the published federal tables. |
| 2026-07-06 | Clinical trials income queried, it sits in a different fund group than last year. |
| 2026-07-09 | Clinical trials treatment confirmed with the controller, prior year restated for comparability. |
| 2026-07-13 | Peer set agreed with the research office, eleven institutions. |
| 2026-07-16 | Draft tables built for all six field of science groupings. |
| 2026-07-20 | Internal QA found two double counted subawards, both corrected. |
| 2026-07-22 | Draft submission assembled and circulated to the research office. |
| 2026-07-27 | First review meeting held, two variance questions raised on subawards. |
| 2026-07-28 | Peer comparison slide added at the associate vice president request. |
| 2026-07-29 | Subaward variance traced to a timing difference, writing it up. |

# Decisions

| Date | Decision | Rationale |
| --- | --- | --- |
| 2026-06-17 | Use finance as the system of record, reconcile sponsored programs to it | Finance figures are what the audit will trace against |
| 2026-06-25 | Exclude cost share bookings from the reconciliation baseline | Cost share is reported separately and was inflating the apparent gap |
| 2026-07-09 | Restate the prior year for the clinical trials fund group change | A year over year comparison is meaningless if the grouping moved between them |
| 2026-07-13 | Fix the peer set at eleven institutions for this cycle | Leadership kept asking for different comparisons, freezing the set makes the trend defensible |
| 2026-07-27 | Report subaward timing differences as a footnote rather than restating | The difference is definitional and reverses next period |

# Links

| Resource | Location |
| --- | --- |
| Reconciliation workbook | Research Compliance / Expenditures / reconciliation |
| Field of science crosswalk | Research Compliance / Expenditures / crosswalk |
| Draft submission | Research Compliance / Expenditures / draft-submission |
| Peer comparison workbook | Research Compliance / Expenditures / peer-comparison |
| Prior year submission as filed | Research Compliance / Expenditures / prior-year-filed |

# Notes

The subaward variance is a timing difference, not an error: finance books on invoice receipt and sponsored programs books on the award period.

Peer comparison is the part leadership always asks about first, so it is worth having ready before the sign off meeting rather than after.

Cost share is reported on its own line of the survey, so it has to stay out of the main reconciliation or the gap reads as roughly twice its real size.

The peer set is frozen for this cycle. Requests to swap institutions mid cycle go to the next one, otherwise the trend stops being comparable to what was filed.