# Space Utilization Study

Project Status: Active, in progress

Unit: Planning and Operations

Report refreshed: 2026-07-29

# Overview

How classroom and lab space is actually used across the week, to support the capital planning process and the current classroom renovation program.

# Project Driving Questions

Question

What proportion of classroom hours are in use, by building and by time of day?

Which rooms are consistently booked but lightly occupied?

Does the current room inventory match the section sizes being scheduled?

# Team

| Name | Role |
| --- | --- |
| Lucia Ferrante | Project lead |
| Nathan Iwu | Analyst |
| Gerald Mbeki | Facilities planning liaison |

# Milestones

| Milestone | Target | Status |
| --- | --- | --- |
| Room inventory reconciled with facilities | 2026-06-05 | Done |
| Scheduled utilization analysis complete | 2026-07-17 | Done |
| Occupancy sampling complete | 2026-08-28 | In progress |
| Capital planning submission | 2026-10-09 | Not started |

# Tasks

| Task | Status |
| --- | --- |
| Reconcile the room inventory with facilities records | Done |
| Analyze scheduled utilization by building and hour | Done |
| Design the occupancy sampling method | Done |
| Run the occupancy sample | In progress |
| Compare room capacity to scheduled section sizes | In progress |
| Write the capital planning submission | Not started |

# Log

| Date | Update |
| --- | --- |
| 2026-06-05 | Room inventory reconciled, 41 rooms had stale capacity figures. |
| 2026-07-17 | Scheduled utilization complete, Tuesday and Thursday mornings are saturated. |
| 2026-07-23 | Occupancy sampling started across four buildings. |
| 2026-07-27 | First sampling week done, booked rooms average 62 percent occupied. |
| 2026-07-29 | Capacity versus section size comparison drafted. |

# Decisions

| Date | Decision | Rationale |
| --- | --- | --- |
| 2026-06-26 | Sample actual occupancy rather than rely on schedule data alone | Scheduled hours overstate real use and would inflate the capital case |

# Links

| Resource | Location |
| --- | --- |
| Utilization analysis | Division Analytics / Space / utilization |
| Room inventory | Facilities / Space / room-inventory |

# Notes

The gap between booked and occupied is the headline. Rooms look full on the schedule and are noticeably emptier in person.

The 41 stale capacity figures matter for the capital case, since several rooms were being scheduled as larger than they now are.